## Backend
Typology | Definition
Site Condition/Availability | Issues on availability of site; inadequacy of existing site structures; unanticipated geological conditions; environmental contamination/liabilities; archaeological and cultural heritage discoveries; right-of-way, land acquisition, and resettlement; peace and order concerns.
Procurement | Delays in procurement and pre-procurement activities (e.g., bidding failure, collapse in negotiations, etc.)
Government/Funding Institution Approvals | Difficulties in obtaining Government or funding institution approvals or required clearances (e.g., issuance of Special Presidential Authority).
Budget and Funds Flow | Delayed or inadequate fund releases; adverse movement of interest or exchange rates; budgetary cuts, etc.
Design, Scope, Technical Specifications | Faulty/inadequate design resulting in facilities which are substandard, unsafe, or incapable of delivering the services at anticipated cost and specified level of service. Includes low demand for outputs (e.g., credit facilities due to uncompetitive relending rates) and changes in scope and output specifications outside the agreed range.
Performance of Contractors/Consultants | Failure of contractor/consultant to provide contracted services to specifications; financial demands on the contractor/consultant exceed its financial capacity.
Capacity of Project Management Unit and Other Implementing Partners | Difficulties in recruitment; turnover of staff affecting program/project implementation; low technical capacity of the PMU to manage/implement the program/project.
Institutional Support | Where the program/project relies on complementary Government, NGO, CSO support, and such support is withdrawn, varied, or deemed inadequate, adversely affecting program/project implementation.
Inputs and Costs | Inputs are unavailable in required quantities or of inadequate quality, or inputs cost more than anticipated, which may be due to price escalation or the effects of inflation, among others.
Legal and Policy Issuances | Where there is a statutory regulation involved, changes are imposed adversely affecting program/project implementation. There may also be a change in law/policy which has adverse consequences on the program/project.
Sustainability, Operations and Maintenance | Formal exit strategies (e.g., on O&M) are not formulated; organizational changes/inadequacies (including O&M budget and manpower) prevent continuity of work or program/project outputs/services/benefits, among others.
Force Majeure | Inability to meet service delivery caused by reason of force majeure events (e.g., earthquake, major typhoons, etc.).
Others | Issues which do not fall under any category cited above
Mode of Implementation
(a) By administration
(b) By Contract
(c) Implemented by the Development Partner/Funding Agency
(d) Coursed through NGOs/CSOs
Sector | Definition
General Public Services | All programs and projects that provide planning, financial, administrative, legal and legislative services to the front-line services of the LGU
Social Services | All programs and projects that promote the well-being and general welfare of constituents or people like education, health, public safety, and protection of the marginalized and disadvantaged members of the society, shall be classified within this sector
Economic Services | All programs and projects directed towards promoting growth in the economy, using all factors in production, like increasing productivity in agriculture and all other industries, generating employment and other livelihood projects
Other Services | All programs and projects that cannot be categorized in any of the sectors identified above

## Form 5
RPMES FORM 5
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
MUNICIPAL PROJECT MONITORING AND EVALUATION COMMITTEE (MPMEC)
MUNICIPALITY OF SANTA CRUZ, LAGUNA, REGION IV-A
SUMMARY OF FINANCIAL AND PHYSICAL ACCOMPLISHMENTS
As of March 31, 2025 (1st Quarter)
Program/Project Title | Implementing Agency | Implementation Schedule |  | Sector | Fund Source | Funding Agency | Total Program/Project Cost (PHP) | Financial Status (in PHP exact figures) | [5 empty] | Physical Accomplishment |  |  | Employment Generated |  | Remarks
|  | Start Date (mm-dd-yyyy) | End Date (mm-dd-yyyy) |  |  |  |  | Appropriations | Allotment | Obligations | Disbursements | Funding Support (%) | Fund Utilization (%) | Target OWPA to date (%) | Actual OWPA to date (%) | Slippage | M | F
Installation of additional security cameras (and other parts) for monitoring of disaster-prone areas | Municipal Disaster Risk Reduction Management Office | 2025-01-10 | 2025-12-31 | Other Services | Others | N/A | 1726690.315 |  |  |  |  | 0 | 0 |  |  | 0 |  |  | Not yet implemented
Procurement of Garbage Truck 20 CBM Collecting 10 Wheeler Dump Truck | Municipal Environment and Natural Resources Office | 2025-04-01 | 2025-04-30 | Social Services | Local Development Fund | N/A | 4200000 |  |  |  |  | 0 | 0 |  |  | 0 |  |  | Not yet implemented
Construction of Elevated Road at Brgy. Sto. Angel Central | Office of the Municipal Engineer | 2025-03-05 | 2025-05-09 | Economic Services | Local Development Fund | N/A | 1500000 | 1500000 | 1500000 | 1500000 | 0 | 100 | 0 | 30 | 90 | 60 | 40 | 0 | The discrepancy in the start and end dates indicated in the form 1 is due to the automatic date formatting feature of Microsoft Excel and Gmail.
Installation of Solar and LED Streetlights at Various Barangay | Office of the Municipal Engineer | 07-01-2025 | 2025-09-30 | General Public Services | Local Development Fund | N/A | 4298543.23 |  |  |  |  | 0 | 0 |  |  | 0 |  |  | Not yet implemented
Construction of Farm-To-Market Road at Sitio Antipolo and Yakal Brgy. Labuin | Office of the Municipal Engineer | 2025-03-05 | 2025-09-11 | Economic Services | Local Development Fund | N/A | 10000000 | 10000000 | 10000000 | 10000000 | 5754564.67 | 100 | 57.5456 | 10 | 70 | 60 | 70 | 0 | The discrepancy in the start and end dates indicated in the form 1 is due to the automatic date formatting feature of Microsoft Excel and Gmail.
Provision of Social Pension Program for Indigent Senior Citizens | Municipal Social Welfare and Development Office | 2025-03-27 | 2025-12-31 | Social Services | Others | N/A | 6000000 | 6000000 | 6000000 | 6000000 | 1000000 | 100 | 16.6667 | 100 | 90.7 | -9.3 | 0 | 0 | The initial payout of the Local Social Pension Program originally scheduled for June 16, 2025 was advanced to March 27, 2025. This adjustment was not only to ensure compliance, but also to provide timely financial and medical support to our indigent Senior Citizens. We acknowledge that 93 beneficiaries were not able to receive their pension during this early payout. Their full entitlement will be carried over to the next release.
Provision of Localized Pantawid Pamilyang Pilipino Program | Municipal Social Welfare and Development Office | 2025-03-27 | 2025-12-31 | Social Services | Others | N/A | 2000000 | 2000000 | 2000000 | 2000000 | 368000 | 100 | 18.4 | 100 | 95.38 | -4.62 | 0 | 0 | This initial payout was made to ensure that our 4Ps beneficiaries receive timely financial assistance in light of pressing needs and to address the upcoming election-related restrictions. We acknowledge that 17 local 4Ps beneficiaries were unable to receive their funds during this payout. Rest assured, their unpaid amount will be included in the next scheduled payout.
Provision of Life Reward grants for Senior Citizens aged 80‒99 years old | Municipal Social Welfare and Development Office | 2025-06-09 | 2025-12-31 | Social Services | Others | N/A | 2000000 |  |  |  |  | 0 | 0 |  |  | 0 |  |  | Not yet implemented
LIVELIHOOD PROGRAM Rice Retailing | Office of the Municipal Agriculturist | 2025-04-01 | 2025-06-30 | Economic Services | Others | N/A | 1000000 |  |  |  |  | 0 | 0 |  |  | 0 |  |  | Not yet implemented
Submitted by: | ENGR. ROSALY M. GUTIERREZ, ENP. | [8 empty] | Approved by: | ENGR. PABLO M. MAGPILY, JR.
Designation/Office: | MUNICIPAL PLANNING AND DEVELOPMENT COORDINATOR CHAIRMAN, MPMEC SECRETARIAT | [9 empty] | MUNICIPAL ENGINEER MPMEC CHAIRMAN
Date: | MAY 7, 2025 | [8 empty] | Date: | MAY 7, 2025

## Form 6
RPMES FORM 6
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
REPORT ON THE STATUS OF PROJECTS ENCOUNTERING IMPLEMENTATION PROBLEMS
As of [Month] [Year] (Quarterly)
Program/Project Title | Location | IA | Fund Utilization (%) | Physical Accomplishment |  |  | Issue Details | Issue Typology | Issue Status | Source of Information | Actions Taken | Actions to be Taken | For NPMC Action (Y/N) | Requested Actions from the NPMC
|  |  |  | Target OWPA to date (%) | Actual OWPA to date (%) | Slippage
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Submitted by: | [5 empty] | Approved by:
Designation/Office: | [6 empty] | Regional Director
Date: | [5 empty] | Date:

## Form 7
RPMES FORM 7
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
PROJECT INSPECTION REPORT
As of [Month] [Year] (Quarterly)
Program/Project Title | Total Program/Project Cost (PHP) | Location | IA | Date of Project Inspection | Details on Site(s) Inspected | Findings |  | Issues | Actions Taken | Actions to be Taken
Submitted by: | [5 empty] | Approved by:
Designation/Office: | [6 empty] | Regional Director
Date: | [5 empty] | Date:

## Form 8
RPMES FORM 8
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
PROBLEM SOLVING SESSIONS/FACILITATION MEETING CONDUCTED
As of [Month] [Year] (Quarterly)
Program/Project Title | Issue Details | Issue Typology | Location | IA | Date of Meeting | Concerned Agencies | Agreements Reached
Submitted by: |  |  |  | Approved by:
Designation/Office: |  |  |  |  | Regional Director
Date: |  |  |  | Date:

## Form 9
RPMES FORM 9
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
TRAINING/WORKSHOP CONDUCTED/FACILITATED/ATTENDED BY THE RPMC
In [Year]
Title of Training/Workshop | Objective of the Training/Workshop | Date | Conducted/ Facilitated/ Attended | Lead Office/ Unit | Participating Offices/ Agencies/ Organizations | Total No. of Participants |  |  | Results and Feedback
[6 empty] | M | F | Total
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Submitted by: |  |  |  | Approved by:
Designation/Office: |  |  |  |  | Regional Director
Date: |  |  |  | Date:

## Form 10
RPMES FORM 10
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
RPMC AND RDC RESOLUTIONS RELATED TO IMPLEMENTATION OF THE RPMES
Resolutions Passed in [Year]
Resolution Number | Resolution Title | Date Approved | Resolution |  | Link to the Resolution
Submitted by: |  |  | Approved by:
Designation/Office: |  |  |  | Regional Director
Date: |  |  | Date:

## Form 11
RPMES FORM 11
REGIONAL PROJECT MONITORING AND EVALUATION SYSTEM (RPMES)
KEY LESSONS LEARNED FROM ISSUES RESOLVED AND BEST PRACTICES
In [Year]
Program/Project Title | Location | Implementing Agency | Problem/ Issue |  | Strategies/Actions Taken to Resolve the Problem/Issue | Responsible Entity/Key Actors and their Specific Assistance | Lessons learned and Good Practices that could be shared to the NPMC/Other PMCs
|  |  | Nature | Details
Submitted by: |  |  |  | Approved by:
Designation/Office: |  |  |  |  | Regional Director
Date: |  |  |  | Date: